## WR_export_2025-03-28_11-56
Street | Town | Ward | Works location description | Works location | Work status | Activity type | Proposed start date | Proposed end date | Works reference number | Promoter | Promoter contact details | Traffic management type
BEDDINGTON FARM ROAD | BEDDINGTON | BEDDINGTON | South from junction of Therapia Lane, and junction of Pylon Way | Carriageway | Works in progress | New service connection | 2025-03-08 | 2025-04-07 | KZ50042224514 | UK POWER NETWORKS | 0800 0280709 | Two-way signals 24hrs
BEDDINGTON LANE | BEDDINGTON | BEDDINGTON | junction with Access Road To 108 To 11 | Carriageway | Works planned | New service connection | 2025-04-13 | 2025-04-13 | NX508FWI3430-SPL | VODAFONE GROUP | 0333 304 0762 | Multi-way signals 09:30 - 16:00
CHURCH ROAD | WALLINGTON | BEDDINGTON | By Lamp post 40m from Junc Croydon Road | Footway, Carriageway | Works in progress | Immediate - emergency | 2025-03-14 | 2025-04-04 | XW063W121289209 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Two-way signals 24hrs
COLLYER AVENUE | BEDDINGTON | BEDDINGTON | Whole road | Carriageway | Works in progress | Highway improvement works | 2025-03-10 | 2025-03-31 | MB00896603648 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 24hrs
COOMBER WAY | BEDDINGTON | BEDDINGTON | O/S Conways | Carriageway | Works in progress | New service connection | 2025-03-17 | 2025-04-07 | KZ50073270666 | UK POWER NETWORKS | 0800 0280709 | Two-way signals 24hrs
PLOUGH LANE | WALLINGTON | BEDDINGTON | FROM O/S 14 TO O/S 98 | Carriageway | Works planned | Highway improvement works | 2025-03-28 | 2025-03-29 | MB00862937789 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 20:00 - 05:00
PLOUGH LANE | WALLINGTON | BEDDINGTON | jcn with Queenwood Avenue | Footway, Carriageway | Works in progress | Highway improvement works | 2025-03-10 | 2025-04-04 | MB00868912342 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Two-way signals 24hrs
QUEENSWOOD AVENUE | WALLINGTON | BEDDINGTON | WHOLE ROAD | Carriageway | Works in progress | Highway improvement works | 2025-03-10 | 2025-04-04 | MB00860436037 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
STAFFORD ROAD | WALLINGTON | BEDDINGTON | OPPOSITE 237B | Footway, Carriageway | Works planned | Utility asset works | 2025-04-07 | 2025-04-11 | DZ001J0HPCN | SES WATER | 01737 772000 | Contra-flow 24hrs
BAWTREE CLOSE | SUTTON | BELMONT | WHOLE ROAD | Carriageway | Works planned | Highway improvement works | 2025-04-04 | 2025-04-04 | MB00842701478 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
BRIGHTON ROAD | SUTTON | BELMONT | junc w/ Chiltern | Carriageway | Works planned | Highway repair and maintenance works | 2025-04-08 | 2025-04-08 | MB00915593572 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Two-way signals
CHILTERN ROAD | SUTTON | BELMONT | Chiltern Road and Brighton Road | Carriageway | Works planned | Highway repair and maintenance works | 2025-04-07 | 2025-04-30 | MB00912186585 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 24hrs
DOWNS ROAD | SUTTON | BELMONT | J/w Cotswold Road to J/w Banstead Road South | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-04-07 | 2025-04-20 | XW016W120973585-05395 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
HEATH DRIVE | SUTTON | BELMONT | SIDE OF 19 CHILTERN ROAD | Carriageway | Works in progress | Immediate - emergency | 2025-03-27 | 2025-04-02 | DZ001J0HPR4 | SES WATER | 01737 772000 | Road closure 24hrs
THE GALLOP | SUTTON | BELMONT | JO Devonshire Road to JO Chiltern Road | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-03-17 | 2025-05-02 | XW016W120973098-02672 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
BANSTEAD ROAD | CARSHALTON | CARSHALTON CENTRAL | From Junction Park Hill To Junction of Harrow Road | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2025-03-17 | 2025-04-20 | XW016W120902281-02087 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
BLAKEHALL ROAD | CARSHALTON | CARSHALTON CENTRAL | Jct of Carshalton Park Road to jct of Glebe road | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-04-21 | 2025-05-26 | XW016W120921270-02123 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
COLSTON AVENUE | CARSHALTON | CARSHALTON CENTRAL | Works outside and opposite No.4 | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-04-08 | 2025-04-14 | DZ001N0HV2N | SES WATER | 01737 772000 | Multi-way signals 24hrs
COWPER AVENUE | SUTTON | CARSHALTON CENTRAL | WHOLE ROAD | Carriageway | Works planned | Highway improvement works | 2025-04-01 | 2025-04-01 | MB00831495676 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
HILL ROAD | CARSHALTON | CARSHALTON CENTRAL | Outside Dr Surgery | Carriageway | Works planned | New service connection | 2025-04-22 | 2025-06-03 | KZ50015935230 | UK POWER NETWORKS | 0800 0280709 | Road closure 24hrs
HILL ROAD | CARSHALTON | CARSHALTON CENTRAL | From jct of Banstead Road 20m into Junction | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-03-21 | 2025-04-15 | XW016W120926112-02389 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
PARK HILL CLOSE | CARSHALTON | CARSHALTON CENTRAL | entire length | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-04-14 | 2025-05-18 | XW016W120921153-02530 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
WALES AVENUE | CARSHALTON | CARSHALTON CENTRAL | From Jct of Harrow Road to Jct of Carlshalton Park Road | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-03-31 | 2025-06-02 | XW016W120920708-2724 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
WEIHURST GARDENS | SUTTON | CARSHALTON CENTRAL | Outside Number 7 | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2025-03-26 | 2025-03-28 | DZ001N0HYJ4 | SES WATER | 01737 772000 | Two-way signals 24hrs
BANSTEAD ROAD | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | 110 Banstead Road. | Carriageway, Verge | Works planned | Utility asset works | 2025-04-22 | 2025-04-27 | DZ001J0H9KV | SES WATER | 01737 772000 | Two-way signals 24hrs
BARROW HEDGES WAY | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | Full length of the Road | Footway, Carriageway, Verge | Works in progress | Utility repair and maintenance works | 2025-02-24 | 2025-04-02 | XW016W120734835-02095 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
BEECHES AVENUE | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | J/w Barrow Hedges Way | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-03-17 | 2025-03-28 | XW016W121295078-02661 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Two-way signals 24hrs
CARSHALTON ROAD | BANSTEAD | CARSHALTON SOUTH & CLOCKHOUSE | ADJ 1 ON CARSHALTON ROAD | Footway | Works planned | Utility asset works | 2025-04-05 | 2025-04-06 | BC410LO00000500346578702 | BT | 03301 233753 | Two-way signals
CENTRAL WAY | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | Full length of the Road | Footway, Carriageway, Verge | Works in progress | Utility repair and maintenance works | 2025-03-03 | 2025-04-17 | XW016W120735174-02189 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
CRANFIELD ROAD EAST | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | SIDE OF 36 PINE RIDGE | Carriageway | Works planned | Utility asset works | 2025-04-03 | 2025-04-07 | DZ001J0J1MP | SES WATER | 01737 772000 | Multi-way signals 24hrs
FAIRWAY | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | Whole Length | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-04-21 | 2025-05-23 | XW016W121051115-02297 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
FARMDALE ROAD | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | Full length of the Road | Footway, Carriageway, Verge | Works in progress | Utility repair and maintenance works | 2025-03-10 | 2025-05-02 | XW016W120735261-02304 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
STANLEY PARK ROAD | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | OUTSIDE 188 | Footway, Carriageway | Works planned | Utility asset works | 2025-04-22 | 2025-04-28 | DZ001J0HPNL | SES WATER | 01737 772000 | Multi-way signals 24hrs
VINCENT AVENUE | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | Whole Length | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-04-14 | 2025-05-16 | XW016W121051184-02722 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
WAVERLEY WAY | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | junction of banstead road | Carriageway | Works in progress | New service connection | 2025-02-24 | 2025-03-28 | KZ50011695295 | UK POWER NETWORKS | 0800 0280709 | Road closure 24hrs
WHITETHORN AVENUE | COULSDON | CARSHALTON SOUTH & CLOCKHOUSE | FROM THE J/W THE MOUNT TO 7-13 | Carriageway | Works planned | Highway improvement works | 2025-03-31 | 2025-03-31 | MB00878282440 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
WOODMANSTERNE LANE | WALLINGTON | CARSHALTON SOUTH & CLOCKHOUSE | o/s 49 to jct with Woodcote Road | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2025-03-03 | 2025-04-21 | XW016W120864772-02777 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Two-way signals 24hrs
ABBOTTS ROAD | CHEAM | CHEAM | J/W Church Hill Road - J/W Matlock Crescent | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-04-07 | 2025-04-20 | XW016W120846003-02806 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
CHEYHAM WAY | CHEAM | CHEAM | From Junction of Cuddington Way to Northey Avenue | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-04-07 | 2025-05-23 | XW016W120981148-02919 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
LUMLEY ROAD | CHEAM | CHEAM | Whole Road | Carriageway | Works planned | Highway improvement works | 2025-04-07 | 2025-04-11 | MB00825302155 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 24hrs
NORTHEY AVENUE | CHEAM | CHEAM | Junction of Shirley Avenue | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-03-31 | 2025-04-14 | XW016W121071254-03225 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
POND HILL GARDENS | CHEAM | CHEAM | o/s 16 | Footway, Carriageway | Works planned | Utility asset works | 2025-04-07 | 2025-04-08 | BC008OGEA12875253SBRC | BT | 03301 233753 | Road closure 09:30 - 15:30
SHIRLEY AVENUE | CHEAM | CHEAM | Outside of 26 to Junction of Warren Avenue | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2025-03-10 | 2025-04-09 | XW016W120979417-03323 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
BUXTON CRESCENT | NORTH CHEAM | NORTH CHEAM | J/W Church Hill Road | Carriageway | Works planned | Highway improvement works | 2025-03-31 | 2025-04-18 | MB00896856937 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 24hrs
BUXTON CRESCENT | NORTH CHEAM | NORTH CHEAM | J/W Wrayfield Road | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2025-03-21 | 2025-03-30 | XW016W120845637-02885 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
CHURCH HILL ROAD | NORTH CHEAM | NORTH CHEAM | o/s 173 | Carriageway | Works planned | Highway improvement works | 2025-04-25 | 2025-04-26 | MB00878608079 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 20:00 - 05:00
CHURCH HILL ROAD | NORTH CHEAM | NORTH CHEAM | j/w BUXTON CRESCENT | Carriageway | Works planned | Highway improvement works | 2025-03-31 | 2025-04-11 | MB00880869609 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Multi-way signals 24hrs
HAYES CRESCENT | NORTH CHEAM | NORTH CHEAM | Whole Length | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2025-03-03 | 2025-04-09 | XW016W120845644-03074 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
WOODBINE LANE | WORCESTER PARK | NORTH CHEAM | jw Cheam common road | Carriageway | Works planned | New service connection | 2025-04-05 | 2025-05-20 | KZ50011637269 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
WRAYFIELD ROAD | CHEAM | NORTH CHEAM | WHOLE ROAD | Carriageway | Works planned | Highway improvement works | 2025-04-22 | 2025-04-23 | MB00833909837 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
WRAYFIELD ROAD | CHEAM | NORTH CHEAM | Whole Length | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2025-02-17 | 2025-04-11 | XW016W120846175-03476 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
FORESTERS DRIVE | WALLINGTON | SOUTH BEDDINGTON AND ROUNDSHAW | OUTSIDE 52 | Footway, Carriageway, Verge | Works planned | Utility asset works | 2025-04-14 | 2025-04-20 | DZ001J0HP9V | SES WATER | 01737 772000 | Multi-way signals 24hrs
THE RIDGE | PURLEY | SOUTH BEDDINGTON AND ROUNDSHAW | 11 to 7 | Carriageway | Works planned | Highway repair and maintenance works | 2025-04-09 | 2025-04-09 | MB00905648426 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
WOODCOTE GREEN | WALLINGTON | SOUTH BEDDINGTON AND ROUNDSHAW | jct with Woodcote Road to jct with Sandy Lane South | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-04-10 | 2025-05-02 | XW016W120869971-02768 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
ST ALBAN'S GROVE | CARSHALTON | ST HELIER EAST | J/W Thornton Road to J/W Shrewsbury Road | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-04-21 | 2025-05-30 | XW016W120894769-05524 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
THORNTON ROAD | CARSHALTON | ST HELIER EAST | O/S 211 to S/O239 and S/O 180 to O/S 234 | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-03-31 | 2025-05-16 | XW016W120887404-01078 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
WELBECK ROAD | CARSHALTON | ST HELIER EAST | From the jcn with Wrythe green to the jcn with Shrewsbury Road | Carriageway | Works planned | Highway improvement works | 2025-04-14 | 2025-04-14 | MB00861751931 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
GREEN WRYTHE CRESCENT | CARSHALTON | ST HELIER WEST | Approx 45m north west of Green Wrythe Lane | Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-04-24 | 2025-04-24 | YN10050996_ERI_STM_ARB | EE Ltd | 01206 430321 | Road closure 10:00 - 14:30
TWEEDDALE ROAD | CARSHALTON | ST HELIER WEST | from the jcn with Wrythe Lane to Paisley Road. | Carriageway | Works planned | Highway improvement works | 2025-04-07 | 2025-04-11 | MB00836107402 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
WELHOUSE ROAD | CARSHALTON | ST HELIER WEST | WHOLE ROAD | Carriageway | Works planned | Highway improvement works | 2025-04-24 | 2025-04-24 | MB00808254817 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
ALBERT ROAD | SUTTON | SUTTON CENTRAL | WHOLE ROAD | Carriageway | Works planned | Highway improvement works | 2025-04-03 | 2025-04-03 | MB00898910498 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
GAUNTLETT ROAD | SUTTON | SUTTON CENTRAL | WHOLE ROAD | Carriageway | Works planned | Highway improvement works | 2025-04-02 | 2025-04-02 | MB00825519005 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
LANGLEY PARK ROAD | SUTTON | SUTTON CENTRAL | under the bridge | Carriageway | Works planned | Highway improvement works | 2025-04-21 | 2025-05-02 | MB00859455150 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
ANGEL HILL | SUTTON | SUTTON NORTH | from outside 11 to outside 77 Angel Hill | Carriageway | Works planned | Highway improvement works | 2025-03-27 | 2025-03-28 | MB00833202438 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Multi-way signals 20:00 - 05:00
STAYTON ROAD | SUTTON | SUTTON NORTH | Works outside and opposite No.55 | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-04-01 | 2025-04-07 | DZ001N0HVF1 | SES WATER | 01737 772000 | Two-way signals 24hrs
VALE ROAD | SUTTON | SUTTON NORTH | WHOLE ROAD | Carriageway | Works planned | Highway improvement works | 2025-04-15 | 2025-04-16 | MB00853370512 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
CHALGROVE ROAD | SUTTON | SUTTON SOUTH | J/W The Ridgway - O/S 15 | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-04-21 | 2025-05-19 | XW016W120721776-02191 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
KAYEMOOR ROAD | SUTTON | SUTTON SOUTH | Whole Length | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-04-07 | 2025-05-19 | XW016W120721552-02411 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
MAYFIELD ROAD | SUTTON | SUTTON SOUTH | Whole Length | Footway, Carriageway, Verge | Works in progress | Utility repair and maintenance works | 2025-02-10 | 2025-04-11 | XW016W120721574-02462 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
PRIOR AVENUE | SUTTON | SUTTON SOUTH | Whole Length | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-04-21 | 2025-06-23 | XW016W120721610-02549 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
THE RIDGWAY | SUTTON | SUTTON SOUTH | Whole Length | Footway, Carriageway, Verge | Works in progress | Utility repair and maintenance works | 2025-03-24 | 2025-05-05 | XW016W120721852-02687 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
WILLIS AVENUE | SUTTON | SUTTON SOUTH | Whole Length | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-04-07 | 2025-05-19 | XW016W120721647-02756 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
GANDER GREEN LANE | SUTTON | SUTTON WEST AND EAST CHEAM | F/W & C/W, OPPOSITE NO 1 | Footway, Carriageway | Works planned | Utility asset works | 2025-04-07 | 2025-04-11 | DZ001J0HT1K | SES WATER | 01737 772000 | Multi-way signals 24hrs
GROVE ROAD | SUTTON | SUTTON WEST AND EAST CHEAM | outside Number 142. | Footway, Carriageway | Works in progress | Immediate - emergency | 2025-03-27 | 2025-04-02 | DZ001N0HYDW | SES WATER | 01737 772000 | Two-way signals 24hrs
GREEN WRYTHE LANE | CARSHALTON | THE WRYTHE | Approx 15m north west of Green Wrythe Crescent | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-04-24 | 2025-04-24 | YN10050996_ERI_STM_ARB2 | EE Ltd | 01206 430321 | Two-way signals 10:00 - 14:30
GREEN WRYTHE LANE | CARSHALTON | THE WRYTHE | junction with Wrythe Green Road | Carriageway | Works planned | Highway improvement works | 2025-04-07 | 2025-04-17 | MB00827418916 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 24hrs
NIGHTINGALE ROAD | CARSHALTON | THE WRYTHE | o/s 125 to 139 | Footway, Carriageway | Works planned | New service connection | 2025-04-07 | 2025-04-16 | KZ50069664482 | UK POWER NETWORKS | 0800 0280709 | Two-way signals 24hrs
ST GEORGES ROAD | WALLINGTON | WALLINGTON NORTH | WHOLE ROAD | Carriageway | Works planned | Highway improvement works | 2025-04-23 | 2025-04-23 | MB00831290782 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
BOUNDARY ROAD | WALLINGTON | WALLINGTON SOUTH | on railway bridge | Carriageway | Works planned | Highway repair and maintenance works | 2025-03-31 | 2025-04-02 | MB00918194669 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Two-way signals 09:30 - 15:00
BRAMBLEDOWN ROAD | WALLINGTON | WALLINGTON SOUTH | J/W Boundary Road - J/W Park Hill Road | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2025-02-24 | 2025-04-08 | XW016W120740082-05455 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
BRAMBLEDOWN ROAD | CARSHALTON | WALLINGTON SOUTH | J/W Boundary Road | Footway, Carriageway, Verge | Works in progress | Utility repair and maintenance works | 2025-02-24 | 2025-03-28 | XW016W120545381-02133 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
WOODCOTE AVENUE | WALLINGTON | WALLINGTON SOUTH | Whole Length | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-04-07 | 2025-05-12 | XW016W120745008-02766 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
WOODCOTE ROAD | WALLINGTON | WALLINGTON SOUTH | CW OS WENDON COURT - SM6 0PR | Carriageway | Works in progress | Immediate - emergency | 2025-03-27 | 2025-04-03 | XW063W121328218 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Two-way signals 24hrs
WOODCOTE ROAD | WALLINGTON | WALLINGTON SOUTH | Woodcote Road from o/s no. 135 to o/s no. 250 | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-04-05 | 2025-04-20 | XW016W120874828-05550 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Two-way signals 24hrs
WOODMANSTERNE LANE | WALLINGTON | WALLINGTON SOUTH | Outside Sherwood Cottage to Woodman/Woodcote Lane | Carriageway | Works in progress | Utility asset works | 2025-03-24 | 2025-04-12 | TV003212570-WOODMANLNE | UK POWER DISTRIBUTION LTD | 08447400074 | Two-way signals 24hrs
BOUNDARY ROAD | CARSHALTON | WALLINGTON SOUTH | J/W Brambledown Road | Footway, Carriageway, Verge | Works in progress | Utility repair and maintenance works | 2025-02-03 | 2025-04-15 | XW016W120545067-05396 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
HALL ROAD | WALLINGTON | WALLINGTON SOUTH | Whole Length | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-04-14 | 2025-05-12 | XW016W120740333-05487 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
HAWTHORN ROAD | WALLINGTON | WALLINGTON SOUTH | Park Hill Road - Woodcote Road | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-04-07 | 2025-05-12 | XW016W120741044-02374 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
HEATHDENE ROAD | WALLINGTON | WALLINGTON SOUTH | J/W Boundary Road - Park Hill Road | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2025-02-24 | 2025-05-02 | XW016W120740980-02379 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
HEATHDENE ROAD | WALLINGTON | WALLINGTON SOUTH | J/W Park Hill Road - Woodcote Road | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-03-10 | 2025-04-14 | XW016W120740820-02379 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
PARK HILL ROAD | WALLINGTON | WALLINGTON SOUTH | J/W Hall Road in FW & CW | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-04-14 | 2025-04-27 | XW016W120743697-02531 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
PARK HILL ROAD | WALLINGTON | WALLINGTON SOUTH | J/W Woodcote Avenue in FW & CW | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-04-07 | 2025-04-21 | XW016W120743629-02531 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
LONGFELLOW ROAD | WORCESTER PARK | WORCESTER PARK NORTH | o/s 268 | Footway | Works in progress | Highway improvement works | 2025-01-06 | 2025-04-25 | MB01311744034 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
DORCHESTER ROAD | WORCESTER PARK | WORCESTER PARK NORTH & NORTH CHEAM | S/O 121 to S/O 111 Langley Avenue | Carriageway | Works planned | Utility repair and maintenance works | 2025-04-07 | 2025-04-20 | XW200W120500483-01452 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
LANGLEY AVENUE | WORCESTER PARK | WORCESTER PARK NORTH & NORTH CHEAM | Junc of Dorchester Road | Carriageway | Works planned | Utility repair and maintenance works | 2025-04-07 | 2025-04-20 | XW200W120500573-01640 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
BALMORAL ROAD | WORCESTER PARK | WORCESTER PARK SOUTH | S/O 2A Hampton Road | Footway | Works planned | Utility asset works | 2025-04-08 | 2025-04-11 | KZ50020205968 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
CHEAM COMMON ROAD | WORCESTER PARK | WORCESTER PARK SOUTH & NORTH CHEAM | os 135 153 | Footway, Carriageway | Works planned | New service connection | 2025-04-05 | 2025-05-20 | KZ50017106402 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs