## WR_export_2025-02-07_09-39
Street | Town | Ward | Works location description | Works location | Work status | Activity type | Proposed start date | Proposed end date | Works reference number | Promoter | Promoter contact details | Traffic management type
BEDDINGTON FARM ROAD | BEDDINGTON | BEDDINGTON | From jw Marlow Way to jw THERAPIA LANE | Carriageway | Works in progress | New service connection | 2025-01-06 | 2025-02-16 | KZ50042224514 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
CENTRAL AVENUE | WALLINGTON | BEDDINGTON | WHOLE ROAD | Carriageway | Works planned | Highway improvement works | 2025-02-21 | 2025-02-22 | MB00866342434 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
COOMBER WAY | BEDDINGTON | BEDDINGTON | Outside 1 COOMBER WAY | Carriageway | Works in progress | New service connection | 2025-02-01 | 2025-02-16 | KZ50093737743 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
COOMBER WAY | BEDDINGTON | BEDDINGTON | From adj 152 to JW BEDDINGTON LANE | Carriageway | Works planned | New service connection | 2025-02-16 | 2025-03-07 | KZ50075177995 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
GOMSHALL AVENUE | WALLINGTON | BEDDINGTON | Whole length of the road | Carriageway | Works planned | Highway improvement works | 2025-02-21 | 2025-02-22 | MB00880414069 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 24hrs
BRIGHTON ROAD | SUTTON | BELMONT | FROM S/O 1-6 DRAPER HSE -CHILTON ROAD TO J/O COTSWOLD ROAD | Footway | Works planned | Highway improvement works | 2025-02-14 | 2025-02-15 | MB00465405892 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Multi-way signals 20:00 - 05:00
BRIGHTON ROAD | SUTTON | BELMONT | Opposite 1-12 Kempston to OS Patcham Court | Carriageway | Works in progress | Immediate - emergency | 2025-01-23 | 2025-02-14 | XW016W121049971-05685 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Two-way signals 24hrs
EGMONT ROAD | SUTTON | BELMONT | Jct of Brighton Road to Jct of Devonshire Road | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2024-09-13 | 2025-02-14 | XW016W120366648-02284 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
THE DOWNSWAY | SUTTON | BELMONT | JO Brighton Road to JO Devonshire Road | Carriageway | Works in progress | Utility repair and maintenance works | 2025-01-13 | 2025-02-28 | XW016W120897812-02669 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
GROSVENOR AVENUE | CARSHALTON | CARSHALTON CENTRAL | Outside 54-20 | Carriageway | Works in progress | New service connection | 2024-11-11 | 2025-02-20 | KZ50017140623 | UK POWER NETWORKS | 0800 0280709 | Two-way signals 24hrs
KINGS LANE | SUTTON | CARSHALTON CENTRAL | FROM J/O UPLAND ROAD TO O/S 1 KINGS LANE | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-02-10 | 2025-03-03 | XW016W120630049-02414 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
BANSTEAD ROAD | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | junction of downside road/waverley way | Footway, Carriageway | Works in progress | New service connection | 2024-12-07 | 2025-02-28 | KZ50056454715 | UK POWER NETWORKS | 0800 0280709 | Two-way signals 24hrs
BARROW HEDGES CLOSE | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | Full length of the Road | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-02-24 | 2025-03-28 | XW016W120734743-02094 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
BARROW HEDGES WAY | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | Full length of the Road | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-02-24 | 2025-03-28 | XW016W120734835-02095 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
BEECHWOOD AVENUE | COULSDON | CARSHALTON SOUTH & CLOCKHOUSE | from junction of Whitethorn ave to o./s No 59 | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-02-17 | 2025-02-28 | XW016W120930508-05622 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
CARSHALTON ROAD | BANSTEAD | CARSHALTON SOUTH & CLOCKHOUSE | o/s The Pastures | Carriageway, Verge | Works planned | New service connection | 2025-02-24 | 2025-03-04 | KZ50013021648 | UK POWER NETWORKS | 0800 0280709 | Road closure 24hrs
CARSHALTON ROAD | BANSTEAD | CARSHALTON SOUTH & CLOCKHOUSE | Carriageway, at the junction of The Pastures | Footway, Carriageway | Works planned | New service connection | 2025-02-11 | 2025-02-13 | DZ001N0H9T0 | SES WATER | 01737 772000 | Two-way signals 24hrs
CARSHALTON ROAD | BANSTEAD | CARSHALTON SOUTH & CLOCKHOUSE | At the junction with Croydon Lane | Carriageway | Works planned | Utility repair and maintenance works | 2025-02-24 | 2025-03-09 | XW016W120871483-02180 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
CENTRAL WAY | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | Full length of the Road | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-03-03 | 2025-04-11 | XW016W120735174-02189 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
CRANFIELD ROAD EAST | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | Whole Length | Footway, Carriageway, Verge | Works in progress | Utility repair and maintenance works | 2025-01-02 | 2025-02-12 | XW016W120545706-02237 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
CROYDON LANE | BANSTEAD | CARSHALTON SOUTH & CLOCKHOUSE | Jct with Woodmansterne Lane / Road to the junction with Fairlawn Road | Carriageway | Works planned | Utility repair and maintenance works | 2025-02-24 | 2025-03-23 | XW016W120876041-02248 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
DOWNSIDE ROAD | SUTTON | CARSHALTON SOUTH & CLOCKHOUSE | Outside no. 2 to junction of banstead road | Carriageway | Works planned | New service connection | 2025-02-10 | 2025-02-28 | KZ50022519507 | UK POWER NETWORKS | 0800 0280709 | Road closure 24hrs
LITTLE WOODCOTE LANE | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | O/S 23 to J/W Lower Pillory Down | Carriageway | Works planned | Utility repair and maintenance works | 2025-01-20 | 2025-02-18 | XW016W120918068-05502 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Two-way signals 24hrs
LITTLE WOODCOTE LANE | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | o/s 67-68 to the junction of Woodmansterne Lane | Carriageway | Works planned | Utility repair and maintenance works | 2025-02-10 | 2025-03-02 | XW016W120858075-05502 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Two-way signals 24hrs
PINE RIDGE | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | Whole Length | Footway, Carriageway, Verge | Works in progress | Utility repair and maintenance works | 2024-12-02 | 2025-02-07 | XW016W120545695-02543 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
STANLEY PARK ROAD | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | OUTSIDE 188 | Carriageway | Works planned | Utility asset works | 2025-02-17 | 2025-02-21 | DZ001J0HPNL | SES WATER | 01737 772000 | Multi-way signals 24hrs
WAVERLEY WAY | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | junction of banstead road | Carriageway | Works planned | New service connection | 2025-02-10 | 2025-02-21 | KZ50011695295 | UK POWER NETWORKS | 0800 0280709 | Road closure 24hrs
WOODMANSTERNE LANE | WALLINGTON | CARSHALTON SOUTH & CLOCKHOUSE | Woodmansterne Lane o/s 49 to jct with Woodcote Road | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-03-03 | 2025-04-21 | XW016W120864772-02777 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Two-way signals 24hrs
WOODMANSTERNE LANE | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | 125m north of Telegraph Track to the junction of Little Woodcote Lane | Carriageway | Works planned | Utility repair and maintenance works | 2025-02-10 | 2025-03-02 | XW016W120850201-05703 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
WOODMANSTERNE LANE | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | Jct Little Woodcote Lane to Woodmansterne Road | Carriageway | Works planned | Utility repair and maintenance works | 2025-02-17 | 2025-03-16 | XW016W120852479-05703 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
LUMLEY ROAD | CHEAM | CHEAM | Whole Road | Carriageway | Works planned | Highway improvement works | 2025-03-03 | 2025-03-07 | MB00825302155 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
NORTHEY AVENUE | CHEAM | CHEAM | O/S 139 | Footway | Works planned | Utility asset works | 2025-03-01 | 2025-03-01 | BC008WG3LRV8YSB | BT | 03301 233753 | Two-way signals 09:30 - 15:30
HILBERT ROAD | NORTH CHEAM | NORTH CHEAM | Whole Length | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-02-17 | 2025-03-24 | XW016W120845700-03092 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
ST MARGARETS AVENUE | NORTH CHEAM | NORTH CHEAM | O/S 103 St. Margarets Avenue, | Footway | Works planned | New service connection | 2025-02-24 | 2025-02-28 | KZ50066069171 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
WRAYFIELD ROAD | CHEAM | NORTH CHEAM | Whole Length | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-02-17 | 2025-04-07 | XW016W120846175-03476 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
THORNTON ROAD | CARSHALTON | ST HELIER EAST | O/S 211 to S/O239 and S/O 180 to O/S 234 | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-03-03 | 2025-04-18 | XW016W120887404-01078 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
FOREST ROAD | SUTTON | STONECOT | junction with Sutton Common Rd, Sutton SM3 9PL | Carriageway | Works planned | Highway improvement works | 2025-02-17 | 2025-02-23 | MB00866714304 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 24hrs
BENHILL AVENUE | SUTTON | SUTTON CENTRAL | 109 | Carriageway | Works planned | Highway repair and maintenance works | 2025-02-18 | 2025-02-18 | MB00929543610 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Multi-way signals 09:30 - 15:00
MONTPELIER ROAD | SUTTON | SUTTON CENTRAL | Outside 2 Hebe Court | Footway, Carriageway | Works planned | Disconnection or alteration of supply | 2025-02-11 | 2025-02-14 | KZ50098086761 | UK POWER NETWORKS | 0800 0280709 | Road closure 24hrs
ST NICHOLAS WAY | SUTTON | SUTTON CENTRAL | S/O St Nicholas Church to O/S St Nicholas way | Footway | Works planned | Utility asset works | 2025-02-11 | 2025-02-13 | BC410LO00000500345967801 | BT | 03301 233753 | Lane closure 24hrs
THROWLEY WAY | SUTTON | SUTTON CENTRAL | Marshalls Road to Benhill Ave | Carriageway | Works planned | Highway repair and maintenance works | 2025-03-05 | 2025-03-07 | MB00827916557 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 21:00 - 05:00
WESTMEAD ROAD | SUTTON | SUTTON CENTRAL | ENTIRE LENGTH | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2025-01-02 | 2025-02-10 | XW016W120499050-02747 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
GRENNELL ROAD | SUTTON | SUTTON NORTH | side of 63 Aultone Way on Grennell Road | Footway, Carriageway, Verge | Works planned | New service connection | 2025-02-17 | 2025-02-21 | DZ001N0FW62 | SES WATER | 01737 772000 | Multi-way signals 24hrs
CEDAR ROAD | SUTTON | SUTTON SOUTH | At the junction of Langley Park Road | Carriageway | Works in progress | New service connection | 2025-02-03 | 2025-02-21 | KZ50083375662 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
HILLCROOME ROAD | SUTTON | SUTTON SOUTH | junction of eaton road to junction of upland road | Carriageway | Works in progress | New service connection | 2025-01-06 | 2025-02-24 | KZ50046327968 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
HILLCROOME ROAD | SUTTON | SUTTON SOUTH | 2b Hillcroome Road | Carriageway | Works planned | Utility asset works | 2025-02-10 | 2025-02-12 | DZ001J0GKGK | SES WATER | 01737 772000 | Two-way signals 24hrs
MAYFIELD ROAD | SUTTON | SUTTON SOUTH | Whole Length | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-02-10 | 2025-03-10 | XW016W120721574-02462 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
THE RIDGWAY | SUTTON | SUTTON SOUTH | Whole Length | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-02-24 | 2025-04-07 | XW016W120721852-02687 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
GANDER GREEN LANE | SUTTON | SUTTON WEST AND EAST CHEAM | Works outside No.174 | Footway, Carriageway | Works in progress | Immediate - urgent | 2025-02-05 | 2025-02-11 | DZ001N0HQLV-A | SES WATER | 01737 772000 | Two-way signals 24hrs
GANDER GREEN LANE | SUTTON | SUTTON WEST AND EAST CHEAM | OPP 145 | Footway, Carriageway | Works in progress | Immediate - urgent | 2025-02-02 | 2025-02-10 | KZ50049252802 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
GANDER GREEN LANE | SUTTON | SUTTON WEST AND EAST CHEAM | from Outside number283 to Outside number 225 | Carriageway | Works planned | Highway improvement works | 2025-03-04 | 2025-03-05 | MB01378276153 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
ERSKINE ROAD | SUTTON | THE WRYTHE | ENTIRE LENGTH | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2025-02-03 | 2025-03-17 | XW016W120426136-02290 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
WEST STREET | CARSHALTON | THE WRYTHE | o/s 119 to jcn with Wrythe Green Road | Carriageway | Works planned | Highway improvement works | 2025-02-15 | 2025-02-19 | MB00886826724 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
WRYTHE GREEN ROAD | CARSHALTON | THE WRYTHE | JCN WITH Wrythe Green lane | Carriageway | Works planned | Highway improvement works | 2025-02-19 | 2025-02-23 | MB00838841392 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 24hrs
WRYTHE LANE | CARSHALTON | THE WRYTHE | O/S 106-109 | Footway | Works planned | Highway improvement works | 2025-02-14 | 2025-02-15 | MB00408559231 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Two-way signals 20:00 - 05:00
BRAMBLEDOWN ROAD | WALLINGTON | WALLINGTON SOUTH | J/W Boundary Road - J/W Park Hill Road | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-02-24 | 2025-04-07 | XW016W120740082-05455 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
BRAMBLEDOWN ROAD | CARSHALTON | WALLINGTON SOUTH | J/W Boundary Road | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-03-02 | 2025-03-31 | XW016W120545381-02133 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure
STAFFORD ROAD | WALLINGTON | WALLINGTON SOUTH | Outside and Opposite 64 Stafford Road. | Footway, Carriageway | Works planned | Utility asset works | 2025-02-17 | 2025-02-23 | DZ001J0GG6Y | SES WATER | 01737 772000 | Two-way signals 24hrs
BOUNDARY ROAD | CARSHALTON | WALLINGTON SOUTH | J/W Brambledown Road | Footway, Carriageway, Verge | Works in progress | Utility repair and maintenance works | 2025-02-03 | 2025-04-15 | XW016W120545067-05396 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
BRIAR BANKS | CARSHALTON | WALLINGTON SOUTH | Whole Length | Footway, Carriageway, Verge | Works in progress | Utility repair and maintenance works | 2025-01-27 | 2025-02-18 | XW016W120545598-02138 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
BRIAR LANE | CARSHALTON | WALLINGTON SOUTH | Whole Length | Footway, Carriageway, Verge | Works in progress | Utility repair and maintenance works | 2025-01-20 | 2025-02-27 | XW016W120545634-02139 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
CHARLOTTE ROAD | WALLINGTON | WALLINGTON SOUTH | Charlotte Road J/W Stafford Road. | Carriageway | Works planned | Utility asset works | 2025-02-17 | 2025-02-23 | DZ001J0GG6YB | SES WATER | 01737 772000 | Road closure 24hrs
CLYDE ROAD | WALLINGTON | WALLINGTON SOUTH | Clyde Road J/W Stafford Road. | Carriageway | Works planned | Utility asset works | 2025-02-17 | 2025-02-23 | DZ001J0GG6YA | SES WATER | 01737 772000 | Road closure 24hrs
DALMENY ROAD | CARSHALTON | WALLINGTON SOUTH | J/W Bramledown Road - O/S 45 | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-02-24 | 2025-03-24 | XW016W120545663-02254 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
HAWTHORN ROAD | WALLINGTON | WALLINGTON SOUTH | Boundary Road - J/W Park Hill Road | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-03-03 | 2025-03-31 | XW016W120740951-02374 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
HAWTHORN ROAD | WALLINGTON | WALLINGTON SOUTH | Park Hill Road - Woodcote Road | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-02-24 | 2025-03-31 | XW016W120741044-02374 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
HEATHDENE ROAD | WALLINGTON | WALLINGTON SOUTH | J/W Boundary Road - Park Hill Road | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-02-24 | 2025-04-28 | XW016W120740980-02379 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
PARK HILL ROAD | WALLINGTON | WALLINGTON SOUTH | J/W Woodcote Avenue in FW & CW | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-03-03 | 2025-03-17 | XW016W120743629-02531 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
PARK HILL ROAD | WALLINGTON | WALLINGTON SOUTH | J/W Hawthorn Road in FW & CW | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-03-03 | 2025-03-17 | XW016W120743343-02531 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
PARK HILL ROAD | WALLINGTON | WALLINGTON SOUTH | J/W Heathdene Road | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-02-24 | 2025-03-10 | XW016W120742785-02531 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
SANDY LANE NORTH | WALLINGTON | WALLINGTON SOUTH and BEDDINGTON | jct with Stafford Road | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-03-09 | 2025-03-09 | YN10053052_ERI_STM_AC | EE Ltd | 01206 430321 | Road closure 10:00 - 15:30
LONGFELLOW ROAD | WORCESTER PARK | WORCESTER PARK NORTH | o/s 268 | Footway | Works in progress | Highway improvement works | 2025-01-06 | 2025-04-25 | MB01311744034 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
CHEAM COMMON ROAD | WORCESTER PARK | WORCESTER PARK SOUTH | 195 NR ST. Matthias RC Church | Footway, Carriageway | Works planned | Utility asset works | 2025-02-23 | 2025-02-23 | BC008WG2R7M8YL2CSB | BT | 03301 233753 | Two-way signals 08:00 - 16:00